## Timeline
VAHAN PROJECT PLAN — 01–25 OCTOBER 2026
No. | Workstream | Task Description | Owner | Start Date | End Date | Status | Acceptance Criteria
1 | Requirements Finalization | Finalize the reporting scope, data requirements, worker count, and acceptance test cases. | Product + Tech Lead + QA | 2026-10-01 | 2026-10-02 | Completed | Agree on the scope, test cases, and acceptance criteria.
2 | Database Design | Create database migrations and table schemas. Persist configurations, jobs, data, and history. | Backend + DevOps | 2026-10-05 | 2026-10-07 | Completed | Store data under the correct dataset and year. Preserve data across restarts.
3 | VAHAN Data Collector | Integrate filter selection, Apply, job-specific CAPTCHA handling, waiting for new results, and Excel downloads. | Automation + Web | 2026-10-01 | 2026-10-09 | Incomplete | Use the correct filters and CAPTCHA challenge. Download all data. Do not classify errors as No data.
4 | Worker Orchestration and Shared Queue | Integrate the SQL-backed queue, 1–10 workers, Run all, Stop/Continue/Restart, and retries. | Backend + Web + DevOps | 2026-10-12 | 2026-10-15 | Incomplete | Run multiple collectors concurrently. Prevent duplicate or lost cases. Change worker count safely. Resume with the correct year and filters. Enforce retry limits.
5 | Excel Data Ingestion | Read all worksheets. Validate context, OTHERS, NULL/0, duplicate imports, and conflicts. Persist data and history. | Backend + QA | 2026-10-14 | 2026-10-16 | Incomplete | Ensure SQL data matches the workbook. Mark a case complete only after a successful transaction commit.
6 | Data Collection Progress Monitoring | Integrate the worker dashboard, Done/Total counts, data/error/retry metrics, Activity/Copy errors, cases/min, ETA, and live updates. | Web + Backend + QA | 2026-10-16 | 2026-10-19 | Incomplete | Track progress by case. Exclude paused time from ETA calculations. Update the UI after each save.
7 | Consolidated Excel Export | Select the dataset and year. Search by State/RTO, view Maker/month data, and export all search results or the entire dataset. | Web + Backend + QA | 2026-10-16 | 2026-10-20 | Incomplete | Apply the same criteria to queries and exports. Export all result pages. Distinguish missing data from zero.
8 | Data Collection Filter Configuration | Integrate profile management, year selection, 15 filter groups, dependencies, caching, Maker search, rules, and case previews. | Web + Backend + Automation | 2026-10-19 | 2026-10-21 | Completed | Save profiles with the correct version. Generate the correct cases. Prevent incorrect cache reuse and interactions with busy workers.
9 | Maker Updates | Capture snapshots, store baselines, identify Maker changes, check State/RTO combinations, and refresh affected cases. | Automation + Backend + Web | 2026-10-20 | 2026-10-22 | Incomplete | Update only changed data. Reconcile the results and support resuming unfinished work.
10 | Data Collection Configuration Validation | Configure daily UI health checks and Check now. Store and view check history, and download CSV reports. | Web + Backend + DevOps | 2026-10-20 | 2026-10-21 | Incomplete | Produce daily reports identifying UI drift and errors. Verify that scheduled checks actually run.
11 | Authentication and Account Management | Create accounts, configure Admin/user permissions, and synchronize user status. | Web + Backend + QA | 2026-10-20 | 2026-10-23 | Incomplete | Enforce permissions. Invalidate sessions on logout or account lock. Restore user status correctly.
12 | Data Search and Lookup | View and search data by date, dataset, and year. Calculate coverage, show missing cases, and support Continue missing. | Web + Backend + QA | 2026-10-19 | 2026-10-22 | Incomplete | Count cases refreshed on the given day correctly. Include valid No data results in coverage. Do not report Complete incorrectly.
13 | Operations Documentation | Document configuration, execution, reporting, Maker updates, troubleshooting, and system limitations. | Tech Lead + QA + DevOps | 2026-10-22 | 2026-10-23 | Not Started | Provide user and operations guides, together with acceptance evidence, for handover.
14 | System Testing | Test integration, regression, access control, the queue, Excel workflows, health checks, and critical error handling. | QA + All Teams | 2026-10-22 | 2026-10-23 | Incomplete | Record test results and resolve blocker defects before acceptance.
15 | System Deployment | Deploy to staging and production. Perform backups and migrations, health checks, monitoring, and rollback. | DevOps + Backend + QA | 2026-10-26 | 2026-10-27 | Not Started | Ensure stable environments. Verify post-deployment checks and rollback.
16 | Acceptance and Handover | Conduct business user acceptance testing (UAT). Hand over configurations, data, and documentation, and obtain release approval. | Product + QA + All Teams | 2026-10-27 | 2026-10-31 | Not Started | Resolve all blockers and reconcile data. Ensure the queue, health checks, SOC, and deployment meet handover criteria.